## CryptIQ_Task_Tracker
Task ID | Task Description | Priority | Status | Dependencies
1 | Complete Module Federation Setup | High | In Progress
1.1 | Configure Module Federation in webpack for all front-end apps | High | Not Started | 1
1.2 | Set up shared components using Module Federation | High | Not Started | 1.1
1.3 | Test Module Federation setup across micro-frontends | High | Not Started | 1.2
2 | API Integration Testing | High | Not Started
2.1 | Write unit tests for API endpoints in cryptiq-shell/api | High | Not Started | 1
2.2 | Perform integration testing between front-end and API | High | Not Started | 1
3 | Complete Frontend Components | Medium | In Progress
3.1 | Implement Dashboard Components | Medium | In Progress
3.1.1 | CryptoDashboardPage.tsx | Medium | Not Started
3.1.2 | MarketScanningDashboard.tsx | Medium | Not Started
3.1.3 | MarketSentimentHeatmap.tsx | Medium | Not Started
3.2 | Implement Portfolio Management Components | Medium | Not Started
3.2.1 | PortfolioAggregation.tsx | Medium | Not Started
3.2.2 | PortfolioRebalancer.tsx | Medium | Not Started
3.2.3 | RiskManagementDashboard.tsx | Medium | Not Started
3.3 | Implement Wallet Components | Medium | Not Started
3.3.1 | ConnectWalletModal.tsx | Medium | Not Started
3.3.2 | ConnectedWalletsList.tsx | Medium | Not Started
4 | Implement Scalability and Performance Enhancements | Medium | Not Started
4.1 | Implement Redis Caching Layer | Medium | Not Started
4.2 | Integrate WebSockets for Real-Time Updates | Medium | Not Started
5 | Enhance Security Measures | High | Not Started
5.1 | Implement API Rate Limiting | High | Not Started
5.2 | Add Two-Factor Authentication (2FA) | High | Not Started
5.3 | Encrypt Sensitive Data at Rest and in Transit | High | Not Started
6 | Develop Comprehensive Testing Strategy | Medium | Not Started
6.1 | Implement Unit Testing | Medium | Not Started
6.2 | Implement Integration Testing | Medium | Not Started
6.3 | Implement End-to-End Testing | Medium | Not Started
6.4 | Set Up Automated UI Tests (Cypress/Selenium) | Medium | Not Started
7 | Set Up Monitoring and Logging Systems | Medium | Not Started
7.1 | Implement Centralized Logging System (ELK Stack) | Medium | Not Started
7.2 | Set Up Application Performance Monitoring (APM) | Medium | Not Started
8 | Create Detailed Documentation | Low | Not Started
8.1 | Create API Documentation (Swagger/OpenAPI) | Low | Not Started
8.2 | Develop Comprehensive Developer Guide | Low | Not Started
9 | Implement Internationalization and Accessibility Features | Low | Not Started
9.1 | Implement i18n Support | Low | Not Started
9.2 | Ensure UI Components are WCAG Compliant | Low | Not Started
10 | Establish CI/CD Pipeline | Medium | Not Started
10.1 | Implement Automated Testing in Pipeline | Medium | Not Started
10.2 | Implement Automated Deployment | Medium | Not Started
11 | Develop Error Handling and Fallback Strategies | Medium | Not Started
11.1 | Implement Graceful Degradation | Medium | Not Started
11.2 | Create Comprehensive Error Handling System | Medium | Not Started
12 | Integrate Advanced Data Visualization Tools | Low | Not Started
12.1 | Integrate D3.js into Data Visualization Components | Low | Not Started
12.2 | Optimize Performance of Data Visualizations | Low | Not Started